## User Stories
Issue type |  | Summary | Priority | Story Point | Assign to
Epic No | story/task No | Registration page
Epic No 1 | Story 1 | Check the user is able to navigate to register page | High | 1 | Ashwini Thigale
| Story 2 | Verify the objects of the register page | High | 2
| Task 1 | Check user is able to enter mobile number/Email Id | High | 1
| Story 3 | Check display of Login using email address button and continue button | Medium | 1
| Story 4 | Check user is able to navigate to the next page | High | 1
| Story 5 | Check the user is receiving an otp on the mobile number/email address | low | 1
| Story 6 | Check the option available to change the mobile number/email address | High | 2
| Story 7 | Check the display of enter otp | high | 3
| Task 1 | Check the user is able to enter the otp | Medium | 2
| Story 8 | Check the display of button for resend otp | High | 1
| Story 9 | Check the button of verify and continue | High | 2
| Story 10 | Check the display objects of registration page | Medium | 1
| Task 1 | Check user is able to insert all required information into the fields
| Task 2 | Validate all the fields by filling and verify if blank spaces are passed in required fields. | High | 2
Epic No | story/task No | Login page
Epic No 2 | Story no 1 | Check the user is able to navigate to login page | High | 3 | Anuradha Gudipati
| Story no 2 | Verifying the objects of the login page | Medium | 1
| Task 1 | Check the Display of enter mobile number or G-mail with text box and continue button | Medium | 3
| Task 2 | Verify the user is able to fill mobile number or G-mail in text box | High | 2
| Task 3 | Check if user enter invalid E-mail/Mobile number then user will get an error message | Medium | 2
| Task 4 | Check user is able to navigate to next page after clicking continue button | Low | 1
| Story no 3 | Validate the signup/login page using either by G-mail/phone number with OTP | High | 3
| Task 1 | verifying the display buttons | Medium | 1
| Task 2 | Check the user is able to change the E-mail/Mobile Number after clicking of continue button | Medium | 2
| Task 3 | Check the user is able to receive otp to their given mobile number/G-mail and able to login using the otp | High | 3
| Task 4 | Check the user is able to receive another otp to their given mobile number/G-mail after clicking of resend button | High | 3
| Story no 4 | Check the user is able to enter data and get successful login | High | 1
| Task 1 | Check if user enter invalid otp then error message displayed to the user | Medium | 1
| Task 2 | Verify that user is able to navigate to home page after successful login. | Medium | 2
Epic No | story/task No | Change Location Page
Epic No 3 | Story 1 | As a user,I should able to display of change location option | High | 3 | Ashwini Yadav
| Task 1 | check user is able to search and select particular city | Medium | 2
| Task2 | check the display of text box to enter area, apartment and pincode | Low | 1
| Task 3 | check the display the continue button | Medium | 2
| Task 4 | check the user is able to the desired location is set | High | 2
| Story 2 | As a user, I should able to display the change location option | High | 1
| Task 1 | check the user is able to display of continue button | Medium | 1
| Task 2 | check the user is able to display of add new | High | 1
| Story 3 | As a User, I should able to navigate to delivery address page | Medium | 2
| Task 1 | check the user is able to Validate all the required fields by filling and Verify if blank spaces are passed in required fields. | High | 2
| Task 2 | check user is able to click on checkbox to save it as default address | Medium | 1
| Task 3 | check the display of Add Address button | High | 1
| Story 4 | check the display of message -"Your address has been saved successfully" | Low | 1
| Story 5 | check the display of Map view | Medium | 1
| Story 6 | check the display of message -Drag the pin to your delivery address. Once you have finalised your delivery location, click on “Confirm Location” | Medium | 1
| Story 7 | check the user is able to move the map pin to desired location | High | 3
| Story 8 | check the display of confirm location button | Medium | 1
| Story 9 | check the user is able to see the address set for delivery | High | 1
Epic No | story/task No | Search Page
Epic No 4 | Story 1 | As a user, I should able to search an item. | High | 2 | Divya Pednekar
| Task 1 | Check the search box and search button is clickable or not | Medium | 0.5
| Task 2 | Check the user is able to enter text in search box | Medium | 0.5
| Task 3 | When user start typing word in text box it should suggest words that matches typed keyword. | Low | 0.5
| Task 4 | Check whether the autopopulated result is having Qty option and add button. | Medium | 0.5
| Story 2 | Check the Search page validation | High | 2
| Task 1 | Verify when hitting the search button without entering anything in the search field and clicking search button then error meaasage should occur. | High | 0.5
| Task 2 | Verify that user should display search page result after clicking on search button with valid search value. | Medium | 0.5
| Task 3 | Check the search result should be relevant to the searched keyword | Medium | 0.5
| Task 4 | Check whether user get the proper validation message when no related products match in search iteam. | Medium | 0.5
| Story 3 | Check categories button on error message page. | Medium | 1
| Task 1 | Check Catagories button is clickable or not. | Medium | 0.5
| Task 2 | Verify all the catagories are disaplyed in bigbasket store page | Medium | 0.5
| Story 4 | Check the Search page items. | High | 3.5
| Task 1 | Check the search iteam displayed with images, name, customer rating, weight, price, qty, & buttons | High | 0.5
| Task 2 | Check after clicking on the item it is redirected to the respective web page | High | 0.5
| Task 3 | Verify that user is able to enter quantity value by clicking on textbox option. | Medium | 0.5
| Task 4 | Verify that quantity is accepting only numbers | High | 0.5
| Task 5 | Verify that user is able to select the weight of the product from the list | Medium | 0.5
| Task 6 | Verify that user is able to click the add button | Medium | 0.5
| Task 7 | Verify if the error message is shown when no Qty or wrong Qty is added in basket | Medium | 0.5
| Story 5 | As a user, I should able to access categoreis Filter panel so that I can view product based on selected filter. | High | 2.5
| Task 1 | Check user is able to select the checkbox from sub categories filter. | Medium | 1
| Task 2 | Verify the search result is displayed based on the selected filter | Medium | 0.5
| Task 3 | Verify the categories option is change according to the product search. | Low | 1
| Story 6 | As a user, I want the sort and show more option. | High | 2
| Task 1 | Verify that all the sort options work correctly and sort the products based on the sort option chosen. | Medium | 1
| Task 2 | Verify the show more option at the bottom page is clickable or not. | Low | 1
Epic No | story/task No | Buy Item
Epic No 5 | Story 1 | Check the user is able to add any item in cart | High | 1 | Alisha Shaikh
| Task 1 | Check user is able to add single item in the cart | Medium | 0.5
| Task 2 | Check user is able to add multiple item in the cart | Medium | 0.5
| Story 2 | As a user I should able to navigate to item description page | High | 1
| Task 1 | check the user is able to add and reduce quantity after clicking plus and minus sign button | Medium | 0.5
| Story 3 | As a user I should able to navigate to delivery address page | High | 1
| Task 1 | check the user is able to change address after clicking change button | Medium | 2
| Task 2 | check the user is able to select which address user prefered for delivery | Medium | 0.5
| Story 4 | As a user I should able to navigate to delivery option page | High | 1
| Task 1 | check the user is able to navigate to payment option page | High | 1
| Task 2 | check the user is able to display two payment methods | High | 1
| Task 3 | check the user is able to navigate to other payment option after clickng other payment option tab | High | 1
| Task 4 | check the user is able to navigate to payment option with offer after clickng payment option with offer tab | High | 1
| Subtask 1 | check the user is able to getting the offer by selecting the particular offer which is available on payment methods | High | 2
| Story 5 | As a user I should able to navigate to confirm order page | High | 1
| Story 6 | As a user I should able to navigate to download and acknowledge the receipt page | High | 1
| Story 7 | As a user I should able to navigate to discount coupon page | High | 1
| Task 1 | check the user is able to apply discount coupon | Medium | 2
| Story 8 | As a user I should able to navigate to offer page | High | 1
| Task 1 | check the user is able to getting the offer by selecting the particular offer which is available on product | Medium | 2

## REGISTRATION
|  |  | Module Name | Registration
|  |  | Done By | Ashwini Thigale
Registration Module
User Story | Functionalities | Test Case ID | Test Case Name | Pre-Requisities | Test Case Steps | Test Data | Expected Result | Actual Result | Status | Additional Comments | Tester
1 | Check the user is able to navigate to the register page | TC_Reg_001 | Validate the Navigation for registration page | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Open any Browser. 2. Enter url: www.bigbasket.com. 3.Click enter on keyboard. 4. Click on login/register button. | https://www.bigbasket.com/ | User Should navigate on registration/login page after clicking on Register/login link. | User can navigate on registration/login page | Pass |  | Ashwini Thigale
2 | Verify the objects of the registration page | TC_Reg_002 | Display the objects of registration page | 1. Open any Browser. 2. Enter url: www.bigbasket.com. 3.Click enter on keyboard. 4. Click on login/register button. | 1.Verifying the logo. 2. Verifying the display of Email text box. 3. Verifying the Login using mobile number and continue button is clickable | NA | All objects should be display after navigating to register page by clicking on the Register/Login Link. | All objects displaying after navigating to register page by clicking on the Register/Login Link. | Pass
3 | Check the user is able to enter valid mobile number/email | TC_Reg_003 | Verify user is able to enter valid mobile number/email. | NA | 1. Click on login/register button 2. Enter valid mobile number/email id | 1234567890 abc@gmail.com | User should be able to enter mobile number/email ID | User is able to enter mobile number/email ID | Pass
4 | Check the user is able to navigate to next page | TC_Reg_004 | Validate the navigation for next page | 1. Mobile number/ email id is entered | 1. Click on continue button | NA | User should navigate to the next page | User is navigating to the next page | Pass
5 | Check the user is receiving an otp on the mobile number/email address | TC_Reg_005 | Validate user is receiving an otp on entered mobile number/email | 1. Mobile number/email is entered. 2. Click on continue button. | 1. Wait for 30 seconds for otp. 2. No otp received 3. Click on resend otp | 310863 | User should receive an otp on entered mobile number/Email ID | User is receiving an otp on entered mobile number/Email ID | Pass
6 | Check the option is availabe and clickable to change mobile number/email address | TC_Reg_006 | Verify the display of option to change mobile number/email address | 1. Mobile number/email is entered. 2. Click on continue | 1. Click on change button 2. Enter another mobile number/email | 1234567890 abc@gmail.com | User should be able to change mobile number/email address | User is able to change mobile number/email address | Pass
7 | Check user is able to enter otp | TC_Reg_007 | Verify user is able to enter otp | NA | 1. Enter otp in the space given. | 345612 | User should be able to enter otp in the given area | User is able to enter otp in the given area | Pass
8 | Check verify and continue button is clickable and navigating to next page | TC_Reg_008 | Validate verify and continue button is clickable and navigating to next page | 1.Mobile number/email is entered 2. Otp is entered | 1. Click on verify and continue button | NA | Verify and continue button should be clickable and navigating to next page | User is able to click on Verify and continue button navigating to next page | Pass
9 | Validate all the Required fields by filling and not filling any data and Verify if blank spaces are passed in required fields. | TC_Reg_009 | Check user is Registered by filling all the fields | NA | 1. Enter valid data in the all the required fields. 2. Click on the start shopping button. | 1. Firstname: Ashwini 2. Lastname: Thigale 3. Email: ashwinithigale31198@gmail.com | User should be registered successful by filling all required fields. | User is registered successful by filling all required fields. | Pass
|  | TC_Reg_010 | Verify it is giving an error message by not filling the details into the fields | NA | 1. Do not fill any data in required fields.. 2. Click on the start shopping button. | 1. Firstname: 2. Lastname: 3. Email: | Should display validation message and display mandatory symbol (*) on all required fields. | Not displaying validation message and not displaying mandatory symbol (*) on first name and last name. | Fail
10 | Check the navigation of start shopping button | TC_Reg_011 | Validate the navigation to home page for shopping | Registration fields are filled correctly | 1. Click on start shopping button | NA | Should navigate to home page for shopping | Navigating to home page for shopping | Pass

## LOGIN
[5 empty] | Module Name | LOGIN
[5 empty] | Done By | ANURADHA GUDIPATI
LOGIN
User Story | Functionality | Test Case ID | Test Case Name | Pre reqiusties | Test Case Steps | Test Data | Excepted Result | Status | Actual Results | Additional Comments | Tester
1 | Check the user is able to navigate to login page | TC_Log_001 | User Navigates to Login page | N/A | 1.Open any browser by entering the url:www.bigbasket.com 2.User navigate to homepage 3.Click on login/sign up button in the home page | url: www.bigbasket.com | User successfully navigates to the bigbasket homepage without any errors. | Pass | user navigates to home page |  | ANURADHA GUDIPATI
2 | Verifying the objects of the login page | TC_Log_002 | Display of Login Page objects | 1.Open any browser by entering the url:www.bigbasket.com 2.User navigate to homepage 3.Click on login/sign up button in the home page | Verify the display of Login page objects 1.Login usingMobile Number textbox 2.Login using E-Mail textbox 3.Continue Button 4.welcome message with LOGIN/SIGNUP | N/A | The following Login page objectives displayed successful to the user 1.E-mail or Phone number text box 2.Continue button. | Pass | Login objectives are displayed
|  | TC_Log_003 | Verify the user is able to fill mobile number or G-mail in text box | Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com | 1.Click on Login in button 2.Enter the E-mail or Mobile number in text-box | E-mail:anu@gmail.com or Mobile Number:+91 9876543214 | The entered E-mail or Mobile Number displayed successfully in the text-box | Pass | user is able to enter E-mail/Mobile Number in text-boxes
|  | TC_Log_004 | Check If user enter invalid E-mail/ Mobile Number it displays an error message | Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com | 1.Enter invalid E-mail address /Mobile Number 2.Click on Continue button | E-mail:abc@gmail.com or Mobile Number:as345567 | If user entered invalid E-mail/Mobile Number error message should be displayed to the user. | Fail | user didn't get any error message and navigates to next page
|  | TC_Log_005 | Check user is able to navigate to next page after clicking continue button | Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com | 1.Enter Valid E-mail address/Mobile Number 2.Click on Continue button | E-mail:anu@gmail.com or Mobile Number:+91 9876543214 | User navigates to Verify E-mail Address page | Pass | User navigates to Verify E-mail page
3 | Validate the signup/login page using either by G-mail/phone number with OTP | TC_Log_006 | Verifying the display buttons | 1.Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com 2.Enter E-Mail address /Mobile Number 3.Click on Continue button | Verify the display of following buttons 1.Change Button 2.Done Button 3.Verify&Continue Button 4.Re-send Button | N/A | The following buttons displays successful to the use: 1.Change button 2.Done button 3.Verify&Continue button 4.re-send button | Pass | change,done ,Verify&continue and re-send buttons displayed successfully
|  | TC_Log_007 | Check the user is able to change the E-mail/Mobile Number by clicking change button | 1.Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com 2.Enter E-Mail address /Mobile Number 3.Click on Continue button | 1.Click on change button 2. Enter different Mobile Number/E-mail which is not equal to previous E-mail/Mobile number 3.Click on done button | E-mail:radha@gmail.com or Mobile Number:+91 8907654321 | User successfully Changed with different E-mail/Mobile Number which is not equl to given E-mail/Mobile number | Pass | User Successfully changed E-mail/Mobile Number
|  | TC_Log_008 | Check the user is able to receive otp to their given mobile number/G-mail and able to login using the otp | 1.Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com 2.Enter E-mail address/Mobile Number 3.Click on continue button | 1.with in 30 sec user will get OTP 2.Open given E-mail or Mobile number and check six digit OTP 3.enter otp 4.Click on verify&Continue | E-mail:anu@gmail.com or Mobile Number:+91 9876543214 otp:567890 | User Successfully get six-digit OTP To their given E-mail or Mobile Number and login successful | Pass | User received OTP to their Mobile Number/E-mail and login successfully
|  | TC_Log_009 | Check the user is able to receive another otp to their given mobile number/G-mail after clicking of resend button | 1.Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com 2.Enter E-mail address/Mobile Number 3.Click on continue button | 1.User didn't received otp after clicking of continue button 2.Click resend OTP button 3.Open given E-mail or Mobile numberand check OTP 4.Enter OTP | Re-send otp:789012 | User get second six-digit OTP To their given E-mail or Mobile Number | Pass | User received another OTP by clicking re-send OTP button
4 | Check the user is able to enter data and get successful login | TC_Log_010 | Check error message is displayed when invalid otp is entered | 1.Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com 2.Enter E-mail address/Mobile Number 3.Click on continue button | 1.Enter invalid otp 2.click on verify &continue button | otp:123456 | User not able to login and gets error meassage as"enter valid otp" | Pass | user not able to Login
|  | TC_Log_011 | Verify that user is able to navigate to home page after successful login. | 1.Navigation to login page by clicking on login from Big Basket home page of the site url:www.bigbasket.com 2.Enter E-mail address/Mobile Number 3.Click on continue button 4.Enter valid OTP | Click on verify&continue button | E-mail:anu@gmail.com or Mobile Number:+91 9876543214 OTP:876543 | User successfully login to BigBasket account and direct to home page for shopping | Pass | User Successfully created account

## LOCATION
|  |  |  | Module Name | Location
|  |  |  | Done By | Ashwini Yadav
Location
User story | Functionality | Test Case ID | Test case Name | Precondition | Test Case Steps | Test Data | Expected Result | Actual Result Iteration 1 | Status
Story 1 | As a user,I should able to display of change location option before login | TC_1 | Check the user is able to search and select is particular city | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on the address option. 2. Enter the city name and select the particular city | Pune | Should able to select the city | Pune was selected | Pass
|  | TC_2 | check the display of text box to enter area, apartment and pincode | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on the address option. 2. Enter the city name and select the particular city" 3.select the text box 4.Enter the area ,apartment and pincode | area-Saswad road. Apartment-Florance pin code-234345 | should able to enter the Area,apartment and pincode | user is able to enter and select the city | Pass
|  | TC_3 | Check the display of continue button | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on the address option. | NA | should able to click on continue button | user is able to click on continue button | Pass
|  | TC_4 | Check the desired location is set | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on the address option. 2. Enter the city name and select the particular city 3.select the text box 4.Enter the area ,apartment and pincode 5.Click on the continue button | Pune saswad road bhekrai nagar pin code-302635 | should able to select desired location | Desired location Pune is set | Pass
story 2 | As a user, I should able to display the change location option after login | TC_5 | Check the display of continue button | 1. Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. | NA | should able to click on continue button | user is able to display continue button | Pass
|  | TC_6 | Check the user is able to click the add new button | 1.Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. | NA | should able to click on add new button | user is able to display the add new | Pass
|  | TC_7 | Check the user is able to display and click view all button | 1.Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2. should be registerd | 1. Click on the address option. 2. Click in view all button. | NA | should able to display and click on view all button | User is able to diplay view all option | Pass
Story 3 | As a user, I should be able to add new address | TC_9 | Check the user is able to navigate to add address page | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. | NA | should able to click on add address page button | user is able to click on add address button | Pass
|  | TC_10 | Verify the user is able to enter the text in all fields | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. 3. enter the details. | First name :Ashwini Last Name: Yadav Address:pune saswad road first floor flat no 102 hp petrol pump | should able to enter thetext in all fields | user is able to enter the following text in the field: First name : Last Name: Address:pune saswad road first floor flat no 102 hp petrol pump | Pass
|  | TC_11 | Verify if the error message is shown when empty required fields are submitted. | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. 3. click on add address button. | First name : Last Name: Address: | show the error message: Enter First name Enter last name Enter address | Displaying the error message: Enter First name Enter last name Enter address | Pass
|  | TC_12 | Check the add address button is clickable or not | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. 3. click on add address button. | NA | should able to click add address button | user is able to click on add address button | Fail
|  | TC_13 | Verify if the user is able to view the map and set the address location | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. 3. click on add address button. | Drag the pin to your delivery address. | should able to see view map and select the address location | user is able to see view map and select the address location | Pass
|  | TC_14 | Verify the confirm location button is clickable. | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. 3. click on add address button. 4. click the Confirm location button | NA | should able to click on confirm location button | user able to click on confirm location button | Pass
|  | TC_15 | Check the Cancel button is clickable or not | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in add new button. 3. click on add address button. | NA | should able to click on cancel button | user able to click on cancel button | Pass
Story 4 | As a user, I Should be able to view all my saved address | TC_16 | Check the user is able to navigate to the View all page | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in view all button. | NA | should able to navigate the view all page | user is able to see view all page | Pass
|  | TC_17 | Check all the address of the user are disaplayed | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in view all button. | NA | should able to display all address | user is able to see the all address | Pass
|  | TC_18 | Check the add address button at the bottom of the view all page is clickable | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in view all button. 3. Click on add address button | NA | should able to click on add address button | user is able to click on add address button | Pass
|  | TC_19 | Check the user is navigated to add address page after clicking add address button under view all page | 1 Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2.user should be registerd | 1. Click on the address option. 2. Click in view all button. 3. Click on add address button | NA | should able to see add address page | user is able to see add address page | Pass

## SEARCH
|  |  | Module Name | Search/ Filter item
|  |  | Done By | Divya Pednekar
Search/Filter page
User Story | Functionality | Test Case Name | Pre-Requisities | Test Case Steps | Test Case id | Test Data | Expected Results | Status | Actual Results | Additional Comments | Tester
1 | As a user, I should able to search an item. | Check the search box and search button is clickable or not | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on the search box. 2. Click on the search button | TC_SEA_01 | NA | Search box and button should be clickable | Fail | After clicking back button search button is not clickable |  | Divya Pednekar
|  | Check the user is able to enter the text in search box | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Enter any text into the search box. | TC_SEA_02 | Coffee | Should able to enter a text into search box | Pass | User is able to enter the text into the search box.
|  | When user start typing word in text box it should suggest words that matches typed keyword and results should have Qty option and add button. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Enter value in search box field. | TC_SEA_03 | Cof | Suggestion should be auto populate with Qty and add button when user start typing. | Pass | Suggestion related to word "Cof" with Qty and add button where autopopulated
2 | Check the Search page validation | Verify when hitting the search button without entering anything in the search field and clicking search button then error meaasage should occur. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on the Search Button | TC_SEA_05 | NA | Should Show error message "No item is searched" | Fail | No error message is shown when clicking on the search button
|  | Verify that user should display search page result after clicking on search button with valid search value. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Enter valid value in search box. 2. Click on the Search button. | TC_SEA_06 | Dairy | Should display search result page | Pass | Dsiplayed search result page.
|  | Check the search result should be relevant to the searched keyword | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Enter valid value in search box. 2. Click on the Search button. | TC_SEA_07 | Dairy | Search result to relevant to the searched Keyword. | Pass | Displayed resultes realted to Dairy product
|  | Check whether user get the proper validation message when no related products match in search iteam. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Enter invalid value in search box. 2. Click on the Search button. | TC_SEA_08 | Textbook | Should get a message "We are sorry, no results found. Please try to search with a different spelling or check out our categories." when no related products match in search iteam. | Pass | Error message is displayed when word "textbook" is searched.
3 | Check categories button on error message page. | Check Catagories button is clickable or not. | 1. Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ 2. Search for invalid value | 1. Click on the Check Catagories button | TC_SEA_09 | Textbook | Check catagoires button should be clickable. | Pass | Check categoires button is clickable
|  | Verify all the catagories are disaplyed in bigbasket store page | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on the Check Catagories button | TC_SEA_10 | NA | Bigbasket store page should list all the catagories. | Pass | Bigbasket store page is listing all the categoreis
4 | Check the Search page items. | Check the search iteam displayed with images, name, customer rating, weight, price, qty, & buttons | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Search for an any item. | TC_SEA_11 | Snacks | Should be able to view all the search item with following data: Image,Name,Customer rating,Weight,Price,Qty and Add Button | Pass | Image,Name,Customer ratingweight,price,Qty and Button all option are displayed in searched item.
|  | Check after clicking on the item it is redirected to the respective web page | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1.Click on any item from searched page. 2. Verify that it is redirected to the respective web page. | TC_SEA_12 | NA | Should be redirected to the respective web page. | Pass | Page is redirected to the respective webpage
|  | Verify that user is able to enter quantity value by clicking on textbox option. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Click on the quantity textbox 2. Enter any number in the box. | TC_SEA_13 | 2 | Should be able to enter quantity number | Pass | User is able to enter any quatity numnber.
|  | Verify that quantity is accepting only numbers | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Click on the quantity textbox 2. Enter any value in the box. | TC_SEA_14 | AB 2#4 | Should not accept any alphabate or symbol | Fail | User is able to add alphabate and symbol
|  | Verify that user is able to select the weight of the product from the list | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Click on the dropdown arrow . 2. Select any weight option from the list | TC_SEA_15 | NA | Should be able to select the weight of the product from the given list. | Pass | User is able to select the weigh of the product from the list
|  | Verify that user is able to click the add button | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Click on the add button | TC_SEA_16 | NA | Should be able to add item to basket after clicking on add button. | Pass | User is able to add item after clicking on add button
|  | Verify if the error message is shown when no Qty or wrong Qty is added in basket | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Click on the add button | TC_SEA_17 | Qty: 0 Qty: ABC | Should show error message "Invalid Quantity " | Pass | Showing error message "Invalid Quantity"
5 | As a user, I should able to access categoreis Filter panel so that I can view product based on selected filter. | Check user is able to select the checkbox from sub categories filter. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Click on any categories checkbox. | TC_SEA_18 | NA | Should be able to select the checkbox from subcategoreis panel filter. | Pass | User is able to select the categories
|  | Verify the search result is displayed based on the selected filter | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Click on any filter checbox | TC_SEA_19 | NA | The page should show the results based on the selected filter. | Pass | Page is showing the result based on the selected filter
|  | Verify the categories option is change according to the product search. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ | 1. Search for valid item. | TC_SEA_20 | Vegetables | The page should show the subcatagories based on the search item. | Pass | The page is show the subcatagories based on the search item.
6 | As a user, I want the sort and show more option. | Verify that all the sort options work correctly and sort the products based on the sort option chosen. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Select the dropdown value | TC_SEA_21 | Sort by: Popularity Price : Low to High Price : High to Low Alphabetical Rupee Saving - High to Low Rupee Saving - Low to High %Off - High to Low | Result should be displayed based on the various sort option. | Pass | Result is displayed based on the various sort option
|  | Verify the show more option at the bottom page is clickable or not. | Navigate to homepage page from any browser using below url: https://www.bigbasket.com/ Search for an valid item | 1. Scroll down at the bottom of the page 2. Click the show more option. | TC_SEA_22 | NA | Show more option at the bottom of the page must show more items related to the search. | Pass | Show more is showing more option after clicking the button

## BUY
|  | Module Name | Buy Item
|  | Done by | Alisha Shaikh
BUY ITEM
User Story | Functionality | Test Case ID | Test case name | Pre Requisites | Test Case Steps | Test Data | Expected Result | Status | Actual Result | Comment | Testers
1 | Check the user is able to add any item in cart | TC_BI_01 | Check user is able to add single item in the cart | 1.Enter url in the browser www.bigbasket.com 2.Search for any item | 1. Enter the product name in the Search text box 2. Click on search icon 3. Select an item from the product items list displayed in search results page 4. In the Product details of that item, click on add to cart button | NA | User Should be able to add single item in the cart | PASS | user is able to add single item |  | Alisha Shaikh
|  | TC_BI_02 | Check user is able to add Multiple item in the cart | 1.Enter url in the browser www.bigbasket.com 2.Search for any item | 1. Enter the product name in the Search text box 2. Click on search icon 3. Select an item from the product items list displayed in search results page 4. In the Product details of that item, click on add to cart button | NA | User Should be able to add multiple item in the cart | PASS | user is able to add multiple item
2 | Check the user is able to navigate to item description page | TC_BI_03 | Navigate to item description page | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Click on view basket and checkout button | 1.Verifying the display of item description | NA | The user should able to navigate to item description page | PASS | User is navigate on item description page
| check the user is able to add and reduce quantity after clicking plus and minus sign button | TC_BI_04 | Add and reduce the Quantity in bascket | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Click on view basket and checkout button 5.Navigate to the item description page | 1.Verifying the display of item description 2.Click on the plus (+) sign for add the quantity 3.Click on the minus (-) sign for reduce the quantity | NA | The user should able to add and reduce item quantity to item description page | PASS | User is add and reduce item quantity on item description page successfully
3 | check the user is able to navigate to delivery address page | TC_BI_05 | Display of delivery address object | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 5.Click on view basket and checkout button 6.Navigate to the item description page 7.Click on checkout button | Verifying display of delivery address i)Personal Details 1.First name 2.Last name 3.Mobile number ii)Address details 1.House number 2.Apartment name 3.Street details 4.Landmark 5.City Name 6.Area details 7.Pincode | NA | User should able to display delivery address objects | PASS | user is see delivery address object
| Check the address page object | TC_BI_06 | The User is able to fill the the first name,Last name and mobile number, house No, area detail textbox in delivery address with mandatry mark | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | 1.Enter the first name in text box 2.Enter the last name in text box 3.Enter the valid mobile number in text box 4.Enter the house number in text box 5.Enter the valid area details in drop down box 6.Enter the pincode | First name:-Alisha Last name:- Shaikh Mobile No:-9021979803 House no:- Banglow no.5 or Flat no. 10 Area details:- Banglore dairy circle Pincode:-560029 | Users should able to enter the first name, last name , mobile number, house number,area details,pincode | PASS | Users is able to enter the following data successfully First name:-Alisha Last name:- Shaikh Mobile No:- 9021979803 House no:- Banglow no.5 or Flat no. 10 Area details:- Banglore dairy circle Pincode:-560029
|  | TC_BI_07 | check the error message is shown when invalid text is entered in first name,last name, phone number, house No. textbox | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | 1.Enter the first name in text box 2.Enter the last name in text box 3.Enter the valid mobile number in text box 4.Enter the house number in text box 5.Enter the valid area details in drop down box | first name:-" " last name:-" " Mobile No:- 9021$#@79& House no:- " " | first name, last name and phone number textbox should not accept blank and other values & display an error message "Please enter a First name" "Please enter a Last name" "Please enter a valid mobile No" "please enter house no" | PASS | it showing an error message "Please enter a First name" "Please enter a Last name" "please enter a valid mobile number" "Please enter house no"
|  | TC_BI_08 | check the area detail and pincode textbox is automatically filled or not | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | 1.Enter the invalid area details in textbox 2.Enter the invalid pincode in textbox box | Area details:-"fghgjbnvbvcgc" Pincode:-5#0@29 | If the user does not enter the correct pincode and area details then it should automatically detect it from the name of the city. | PASS | If the user does not enter the correct pincode and area details then it should automatically detect it from the name of the city.
|  | TC_BI_09 | The User is able to fill the the city name,apartment name, street details and landmark in delivery address | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | 1.Enter the city name in drop down box 2.Enter the apartment name in test box 3.Enter the street details in text box 4.Enter the landmark details in text box | City name:- Banglore apartment name:-"sai apartment" Street details:-"Gurudwara road" landmark:-"near water tank" | Users should able to enter the city name, apartment name,street details and landmark | PASS | user is enter the city name ,apartment name, street details and landmark successfully
| check the user is able to change address after clicking change button | TC_BI_10 | user is able to Change Address | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | 1.Click on change button 2.Enter maindatory field 3.Click on add address | NA | User should able to change address in delivery address page | PASS | user is change the address in delivery page successfully
| check the user is able to select which address user prefered for delivery | TC_BI_11 | user is able to Select Address | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | 1.if there is multiple address is present Select which address user Required 2. click on delivery here button | NA | User should able to select address in delivery address page | PASS | user is select the address in delivery page successfully
4 | check the user is able to navigate to delivery option page | TC_BI_12 | Navigate to delivery option page | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | 1.if there is multiple address is present Select which address user Required 2. click on delivery here button 3.Navigate to delivery option page | NA | User should able to navigate to delivery option | PASS | User is navigate on delivery option Succressfully
5 | check the user is able to navigate to payment option page | TC_BI_13 | Navigate to Payment Option | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page | On delivery option page 1.Click on proceed to payment button 2.Navigate to payment option page | NA | User should able to navigate to payment option | PASS | User is navigate on payment option successfully
6 | check the user is able to display two payment methods | TC_BI_14 | Display two methods of payment | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.Navigate to payment option page by clicking proceed to payment button | On payment option page 1.It shows two tabs i)Payment option with offers ii)Other payment option | NA | User should able to display methods of payment | PASS | User is see methods of payment
7 | check the other payment option tab | TC_BI_15 | Navigate to other payment option tab | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.Navigate to payment option page by clicking proceed to payment button | On payment option page 1.It shows two tabs i)Other payment option ii)Payment option with offers 2.Click on the other payment option | NA | User should able to navigate to Other payment option page | PASS | User is navigate on other payment option page successfully
|  | TC_BI_16 | verify the user is able to enter credit/debit card details | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.Navigate to payment option page by clicking proceed to payment button | On payment option page 1.It shows two tabs i)Other payment option ii)Payment option with offers 2.Click on the other payment option 3.Enter the all credit/debit card details | Card no:- 4351 4365 4398 6508 valid thru:- 22/25 CVV:-508 | user should able to submit credit/debit card data | PASS | user is able to submit credit/debit card data successfully
|  | TC_BI_17 | check the error message is displayed when user enter invalid credit/debit card details | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.Navigate to payment option page by clicking proceed to payment button | On payment option page 1.It shows two tabs i)Other payment option ii)Payment option with offers 2.Click on the other payment option 3.Enter the all credit/debit card details | Card no:- 5647 4365 4398 6508 valid thru:- 22/25 CVV: 508 | The following error should be displayed: 1. Enter valid card number 2. Inavlid expiry date | PASS | The following errors are displaying 1. Enter valid card number 2. Inavlid expiry date
8 | check the payment option with offer tab | TC_BI_18 | Navigate to payment option with offer tab | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.Navigate to payment option with offer tab page by clicking proceed to payment button | On payment option page 1.It shows two tabs i)Other payment option ii)Payment option with offers 2.Click on the Payment option with offers option 3.Navigate to Payment option with offers tab | NA | User should able to navigate to payment option with offer page | PASS | User is navigate on payment option with offer page
|  | TC_BI_19 | Display offers in payment option with offer tab | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.Navigate to payment option with offer tab page by clicking proceed to payment button | On payment option page 1.It shows two tabs i)Other payment option ii)Payment option with offers 2.Click on the Payment option with offers option 3.Navigate to Payment option with offers tab 4.Click on any one payment option | NA | User should able to get offer on payment method | PASS | user is getting offers on payment methods
9 | Check the discount coupon page | TC_BI_20 | Check the display of discount coupon page | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button | After Navigating to the delivery address page 1.Click on discount available button | NA | User should able to dsiplay discount coupon page | PASS | user is able to display on discount coupon page
|  | TC_BI_21 | Check the user is able to enter the code and select from available discount | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.5.Click on discount available button | After Navigating to the delivery address page 1. Enter voucher code or Click on discount available button 2.Click on apply | NA | User should able to apply discount on product | PASS | user is able to apply discount on product
10 | check the user is able to navigate to confirm order page | TC_BI_22 | Navigate to confirm order page | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.click on any one payment method | After selecting any one payment method 1.Navigate to confirm order page 2.Click on confirm order button | NA | User should able to navigate to confirm order page and confirm it | PASS | User is navigating on confirm order page and successfully confirm it
11 | check the user is able to navigate to download and acknowledge the receipt page | TC_BI_23 | Navigate to download and acknowlege the receipt page | 1.Enter url in the browser www.bigbasket.com 2.Select product and add to the cart 3.Navigate to shopping cart 4.Navigate to the item description page by clicking view basket and checkout button 5.Navigate to delivery address page by clicking checkout button 6.Navigate to delivery option page 7.Navigate to confirm order by clicking any one payment method 8.click on the confirm order button | After Clicking on confirm order button 1.Navigate to download and acknowlege the receipt page 2.Click on download button | NA | User should able to navigate to download and acknowlegethe receipt page and should download it | PASS | User is navigating on download and acknowlege the receipt page and successfully download it
12 | check the user is able to navigate to offer page | TC_BI_24 | Navigate to offer page | 1.Enter url in the browser www.bigbasket.com | Click on the offers tab which are displayed on the home page | NA | User should able to navigate to offers page | PASS | user is navigate on offers page
13 | check the user is able to getting the offer by selecting the particular product | TC_BI_25 | Display offers in offer tab | 1.Enter url in the browser www.bigbasket.com 2.Navigate to offer page | 1.Click on the offers tab which are displayed on the home page 2.Select your offer | NA | User should able to get offers from offer page | PASS | user is get offers

## Defect Report
Defect ID | MODULE NAME | DEFECT SUMMARY | PRIORITY | ASSIGNEE | REPORTER | STATUS
DF_001 | Registration | For blank fields not displaying validation message and not displaying mandatory symbol (*) for the first name and last name. | Low |  | Ashwini Thigale | To Do
DF_002 | Login | System navigates to OTP page even with invalid E-mail address/Mobile Number | High |  | Anuradha Gudipati | To Do
DF_003 | Location | After clicking add address button is not clickable | High |  | Ashwini Yadav | To Do
DF_004 | Search/filter item | After clicking back button search button is not clickable | Medium |  | Divya Pednekar | To Do
DF_005 | Search/filter item | it should show error message"No item is searched" but No error message is shown when clicking on the search button | High |  | Divya Pednekar | To Do
DF_006 | Search/filter item | it should not accept any alphabate or symbolbut user is able to add alphabate and symbol | High |  | Divya Pednekar | To Do

## TM_Register
REQ_ID | REQ DESCRIPTION | TEST CASE ID | TEST CASE DESCRIPTION | EXECUTION STATUS | DEFECT ID | DEFECT STATUS
RQ_01 | Navigation for registration page | TC_Reg_001 | Validate the Navigation for registration page | Pass
RQ_02 | Display the objects of registration page | TC_Reg_002 | Verify the display objects of the registration page | Pass
RQ_03 | Validate the mobile number/email field | TC_Reg_003 | Verify user is able to enter valid mobile number/email. | Pass
RQ_04 | Navigation to next page | TC_Reg_004 | Validate the navigation for next page | Pass
RQ_05 | Mobile number/Email Validation with otp | TC_Reg_005 | Validate user is receiving an otp on entered mobile number/email | Pass
RQ_06 | Validate the buttons are displayed and working | TC_Reg_006 | Verify the display of option to change mobile number/email address | Pass
|  | TC_Reg_008 | Validate verify and continue button is clickable and navigating to next page
RQ_07 | Validate Enter otp field | TC_Reg_007 | Verify user is able to enter otp | Pass
RQ_08 | Validate the fields | TC_Reg_009 | Check user is Registered by filling all the fields | Pass
|  | TC_Reg_010 | Verify it is giving an error message by not filling the details into the fields | Fail | DF_001 | To Do
RQ_09 | Navigation to home page for shopping | TC_Reg_011 | Validate the navigation to home page for shopping | Pass

## TM_Login
REQ_NO | REQ_DESCRIPTION | TESTCASE_ID | TEST CASE_DESCRIPTION | EXECUTION_STATUS | DEFECT_ID | DEFECT_STATUS
REQ_1 | Navigate to login page | TC_Log_001 | Navigates to Login page | PASS
REQ_2 | Display of Login page Objects | TC_Log_002 | Display of Login Page objects | PASS
REQ_3 | Validate the mobile number/E-mail address field | TC_Log_003 | Verify the user is able to fill mobile number or G-mail in text box | PASS
REQ_4 | Validate the mobile number/E-mail address | TC_Log_004 | Check If user enter invalid E-mail/ Mobile Number it displays an error message | FAIL | DF_002 | TO DO
REQ_5 | Navigation to next page | TC_Log_005 | Check user is able to navigate to next page after clicking continue button | PASS
REQ_6 | Validate the display and working of buttons | TC_Log_006 | Verifying the display buttons | PASS
|  | TC_Log_007 | Check the user is able to change the E-mail/Mobile Number by clicking change button | PASS
REQ_7 | OTP Validation | TC_Log_008 | Check the user is able to receive otp to their given mobile number/G-mail and able to login using the otp | PASS
|  | TC_Log_010 | Check error message is displayed when invalid otp is entered | PASS
REQ_8 | After login validate navigation to home page | TC_Log_011 | Verify that user is able to navigate to home page after successful login. | PASS

## TM_Location
REQ_ID | REQ DESCRIPTION | TEST CASE ID | TEST CASE DESCRIPTION | EXECUTION STATUS | DEFECT ID | DEFECT STATUS
REQ_1 | display of location option | TC_1 | Verify the display of location option | Pass
REQ_2 | To verify user is able to search and select is particular city | TC_2 | Check the display of text box to enter area, apartment and pincode | Pass
REQ_3 | Display the continue button | TC_3 | Check the display of continue button | Pass
REQ_4 | set the desired location | TC_4 | Check the desired location is set | Pass
REQ_5 | Display the continue button | TC_5 | Check the display of continue button | Pass
REQ_6 | verify the add new button clickable or not | TC_6 | Check the user is able to click the add new button | Fail | DF_1 | To_Do
REQ_7 | verify the view all button display and clickable or not | TC_7 | Check the user is able to display and click view all button | Pass
REQ_8 | Navigate add address page | TC_8 | Check the user is able to navigate to add address page | Pass
REQ_9 | verify enter the text in all fields | TC_9 | Verify the user is able to enter the text in all fields | Pass
REQ_10 | verify the error message show or not | TC_10 | Verify if the error message is shown when empty required fields are submitted. | Pass
REQ_11 | verify add address button clickable or not | TC_11 | Check the add address button is clickable or not | Pass
REQ_12 | verify the view map | TC_12 | Verify if the user is able to view the map and set the address location | Pass
REQ_13 | verify confirm location button clickable or not | TC_13 | Verify the confirm location button is clickable. | Pass
REQ_14 | verify cancel button clickable or not | TC_14 | Check the Cancel button is clickable or not | Pass
REQ_15 | navigate view all page | TC_15 | Check the user is able to navigate to the View all page | Pass
REQ_16 | verify all address displayed | TC_16 | Check all the address of the user are disaplayed | Pass
REQ_17 | verify add address button clickable or not | TC_17 | Check the add address button at the bottom of the view all page is clickable | Pass
REQ_18 | verify navigate add address page | TC_18 | Check the user is navigated to add address page after clicking add address button under view all page | Pass

## TM_Search
REQ_ID | REQ DESCRIPTION | TEST CASE ID | TEST CASE DESCRIPTION | EXECUTION STATUS | DEFECT ID | DEFECT STATUS
REQ_01 | Click on Search tab | TC_SEA_01 | Verify search box and search button is clickable or not | Fail | DF_004 | TODO
|  | TC_SEA_02 | Verify the user is able to enter the text in search box | Pass
|  | TC_SEA_03 | Verify that suggestion should be autopopulated and should have Qty and add button | Pass
|  | TC_SEA_05 | Verify the error message is displayed when user try to search empty value | Fail | DF_005 | TODO
REQ_02 | Verify search page result | TC_SEA_06 | Verify the display search page result | Pass
|  | TC_SEA_07 | Verify the search page result is relevent ot searched keyword | Pass
REQ_03 | Validation message | TC_SEA_08 | Verify the validation messages when no product matches the searrch item | Pass
REQ_04 | Verify categories button on error message page | TC_SEA_09 | Verify the categoreis button is clickable | Pass
|  | TC_SEA_10 | Verify all the catagories are disaplyed in bigbasket store page | Pass
REQ_05 | Verify the search page items. | TC_SEA_11 | Product details should be visible for all search iteams. | Pass
|  | TC_SEA_12 | Verify after clicking on the item it is redirected to the respective web page | Pass
REQ_06 | Validate the options on search page | TC_SEA_13 | Verify that user is able to enter quantity value by clicking on textbox option. | Pass
|  | TC_SEA_14 | Verify that quantity is accepting only numbers | Fail | DF_006 | TODO
|  | TC_SEA_15 | Verify that user is able to select the weight of the product from the list | Pass
|  | TC_SEA_16 | Verify that user is able to click the add button | Pass
|  | TC_SEA_17 | Verify if the error message is shown when no Qty or wrong Qty is added in basket | Pass
REQ_07 | Verify the sub categories Filter | TC_SEA_18 | Verify the checkbox from subcategories filter | Pass
|  | TC_SEA_19 | Verify the search result is displayed based on the selected filter | Pass
REQ_08 | Verify all checkbox | TC_SEA_20 | Verify the categories option is change according to the product search. | Pass
REQ_09 | Verify all sorting options | TC_SEA_21 | Verify that all the sort options work correctly and sort the products based on the sort option chosen. | Pass
REQ_10 | Verify Show more option | TC_SEA_22 | Verify the show more option at the bottom page is clickable or not. | Pass

## TM_BuyItem
REQ_ID | REQ DESCRIPTION | TEST CASE ID | TEST CASE DESCRIPTION | EXECUTION STATUS | DEFECT ID | DEFECT STATUS
REQ_ID 1 | Add item in cart | TC_BI_01 | Verify the user is able to add single item in the cart | PASS
|  | TC_BI_02 | Verify the user is able to add Multiple item in the cart | PASS
REQ_ID 2 | Navigate to Item Description page | TC_BI_03 | Verify the user is able to Navigate to item description page | PASS
REQ_ID 3 | Add and reduce quantity in bascket | TC_BI_04 | Verify the user is able to Add and reduce the Quantity in bascket | PASS
REQ_ID 4 | Display of delivery address object | TC_BI_05 | Verify the user is able to Display of delivery address object | PASS
REQ_ID 5 | Validate the delivery address object | TC_BI_06 | Verify the user is able to fill all mandatory information in delivery address with mandatry mark | PASS
|  | TC_BI_07 | Verify the error message is shown when invalid text is entered in delivery address with mandatory mark | PASS
|  | TC_BI_08 | Verify the area detail and pincode textbox is automatically filled or not | PASS
|  | TC_BI_09 | Verify the user is able to fill the the city name,apartment name, street details and landmark in delivery address | PASS
|  | TC_BI_10 | Verify the user is able to Change Address | PASS
|  | TC_BI_11 | Verify the user is able to Select Address | PASS
REQ_ID 6 | Navigate to delivery option page | TC_BI_12 | Verify the user is able to Navigate to delivery option page | PASS
REQ_ID 7 | Validate the payment option | TC_BI_13 | Verify the user is able to Navigate to Payment Option | PASS
|  | TC_BI_14 | Verify the user is able to Display two methods of payment | PASS
|  | TC_BI_15 | Verify the user is able to Navigate to other payment option tab | PASS
|  | TC_BI_16 | verify the user is able to enter credit/debit card details | PASS
|  | TC_BI_17 | Verify the error message is displayed when user enter invalid credit/debit card details | PASS
|  | TC_BI_18 | Verify the user is able to Navigate to payment option with offer tab | PASS
|  | TC_BI_19 | Verify the user is able to Display offers in payment option with offer tab | PASS
REQ_ID 8 | Validate the discount coupon | TC_BI_20 | Verify the user is able to display of discount coupon page | PASS
|  | TC_BI_21 | Verify the user is able to enter the code and select from available discount | PASS
REQ_ID 9 | Confirm order | TC_BI_22 | Verify the user is able to Navigate to confirm order page | PASS
REQ_ID 10 | Download and acknowlege receipt | TC_BI_23 | Verify the user is able to Navigate to download and acknowlege the receipt page | PASS
REQ_ID 11 | Display offer in offer tab | TC_BI_24 | Verify the user is able to Navigate to offer page | PASS
|  | TC_BI_25 | Verify the user is able to Display offers in offer tab | PASS

## Test Summary report
Test Summary Report
Test Cycle System Test
EXECUTED | 88 | PASSED | 82
|  | FAILED | 6
(Total)TESTS EXCUTED (PASSED+FAILED)
PENDIING |  | 0
IN PROGRESS |  | 0
BLOCKED |  | 0
(Sub-Total) TEST PLANNED |  | 0
(PENDING+INPROGRESS+BLOCKED+TEST+EXECUTED) |  | 88
Function | Description | No of TCs Executed | No of TCs Passed | TCs pending | Priority | Remarks
Register Functionalities | Verify that user should be able to register to https://bigbasket.com/ successfully | 11 | 10 | 0 | High
Login Functionalities | Verify that user should be able to login to https://bigbasket.com/ successfully | 11 | 10 | 0 | High
Change Location Functionalities | Verify that user should be able to change location successfully | 19 | 18 | 0 | High
Search item Functionalities | Verify that user should be able to search item succesfully | 22 | 19 | 0 | High
Buy Item Functionalities | Verify that user should be able to buy item successfully | 25 | 25 | 0 | High